## Action Items
ACTION ITEMS TRACKER
Item ID | Description | Owner | Status | First Mentioned | Last Updated | Notes
AI-001 | Pull all available data from the database using existing scripts; explore all accessible tables and fields beyond the two currently used variables | Ajer / Liam | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Ajer confirmed: 'We were able to pull all the data from the SQL database.' Data extracted in Python.
AI-002 | Run statistical analyses (correlation matrices, covariance, etc.) in Python to identify variables most predictive of loan funding | Ajer / Liam | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Ran correlation/feature-importance analysis. Pipeline stage = 59.5% predictive power; days at stage = 9.9%; days remaining in month = 8.4%; credit score, loan amount, lock period ~3-4% each.
AI-003 | Prioritize adding 'product' and 'purpose' variables to the predictive model as first enhancement step | Ajer / Liam | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Added and validated. Purchase loans fund 6% of time vs refi cashout 47%; FHA purchase 64%. Confirmed up to 59pp shift in probabilities. Augie confirmed this was the right call.
AI-004 | Build an improved predictive model focusing on the most influential variables (avoid adding too many to prevent noise) | Ajer / Liam | In Progress | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Two models running (transition table + gradient boosting ML). Calibration issues found; product/purpose variables embedded in pipeline stage feature — Augie flagged this needs to be decoupled. New action items added.
AI-005 | Back-test the model: use historical data up to a cutoff date (e.g. Dec 2024) to predict a subsequent period (e.g. Jan 2025) and compare vs. actuals | Ajer / Liam | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Back-tested on all 24 months of 2024-2025. Avg error at mid-month: 6.4%. 18/24 months within 10% of actual. Nov/Dec 2025 were outliers (28% and 16% over-projection). Framework confirmed valid, refinement needed.
AI-006 | Run multiple model methodologies (3–5 models) and compare predictive power across them before selecting the best approach | Ajer / Liam | In Progress | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Two models running: transition table and gradient boosting. Augie confirmed this is correct direction. More tuning and comparison needed.
AI-007 | Add campus Wi-Fi IP address to database whitelist for Ajer and Liam | Mariana / Israel | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | No issues with database access reported in Call 2. Assumed resolved.
AI-008 | Add Liam to the Forecasting Slack channel | Augie (Admin) | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Liam participated actively in Call 2, implying Slack/comms access was resolved.
AI-009 | Share the call recording with Ajer and Liam after the Zoom session ends | Mariana | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | No issues raised in Call 2. Assumed completed after Call 1.
AI-010 | Review the existing model scripts (sent by Mariana/Israel) to understand current data structure, pipeline logic, and variables used | Ajer / Liam | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Team demonstrated deep understanding of pipeline logic, SQL structure and existing model. Confirmed reviewed and internalized.
AI-011 | Set up weekly Wednesday catch-up calls; confirm recurring time works for Augie or adjust based on his availability | Mariana / Ajer | Completed | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Call 2 held on schedule. Weekly cadence confirmed operational.
AI-012 | Eventually integrate funding projections with P&L and balance sheet to show clients projected loan volume, revenue, and cash impact | Augie / Team | In Progress | Call 1 – Apr 14, 2026 | Call 2 – Feb 18, 2026 | Augie showed his corporate finance model live and explicitly confirmed this is the end goal. Elevated to active roadmap item, not just future-phase.
AI-013 | Fix back-test methodology: use pipeline snapshot as of last day of prior month (e.g. use Oct 31 data to project Nov; Nov 30 data to project Dec). Do NOT use mid-month pipeline for full-month projection. | Ajer / Liam | Completed | Call 2 – Feb 18, 2026 | Call 3 – Feb 25, 2026 | Implemented. All 24 months now use end-of-prior-month snapshot (Dec←Nov30, Nov←Oct31). Confirmed by Ajer in Call 3. Consistent framework locked in.
AI-014 | Investigate and explain November & December 2025 outlier errors (28% and 16% over-projection). Determine if rate environment, seasonality, or data issue caused the anomaly. | Ajer / Liam | In Progress | Call 2 – Feb 18, 2026 | Call 3 – Feb 25, 2026 | Nov 2025 error reduced from 28%→18%→13% via rolling window. Dec 2025 from 15%→6%. Nov still above 10% target. Root cause not fully resolved. Rolling window was the main fix, not lock features.
AI-015 | Decouple 'product' and 'purpose' from the pipeline stage probability feature so each variable shows its own independent explanatory power in the feature importance chart. | Ajer / Liam | Completed | Call 2 – Feb 18, 2026 | Call 3 – Feb 25, 2026 | Done. Product and purpose are now independent features. Standalone weight is small (signal already captured by pipeline stage) but they are now visible and transparent for client reporting. Non-conforming purchase=60%, FHA purchase=64%, refi cashout=47%.
AI-016 | Add 'rate lock date' and 'lock expiration date' as new model variables. Compute delta between lock expiration date and today, and between loan creation date and lock date. | Ajer / Liam | Completed | Call 2 – Feb 18, 2026 | Call 3 – Feb 25, 2026 | 5 new lock features built. Lock expiry vs month end = 60% of model weight in V2. Mid-month error improved 6.5%→4.8%. Augie confirmed: always use lock data, no model without it. Version B (with lock) chosen.
AI-017 | Explore whether seasonality (summer vs winter months) has explanatory power on loan funding speed and volume. Consider adding month-of-year or quarter as a variable. | Ajer / Liam | Completed | Call 2 – Feb 18, 2026 | Call 3 – Feb 25, 2026 | Tested. Summer pull-through=41% vs winter=36%. Volume 25% higher in summer. Key finding: days-to-fund is FLAT year-round — it's conversion rate that shifts, not speed. Available as next feature if desired.
AI-018 | Apply model calibration to fix overconfidence in mid-range probability loans (loans scored ~55% actually fund ~40-47%). Investigate standard statistical recalibration techniques (e.g., Platt scaling, isotonic regression). | Ajer / Liam | In Progress | Call 2 – Feb 18, 2026 | Call 4 – Mar 4, 2026 | Not explicitly addressed. 4.8% error accepted by Augie as sufficient. Formal recalibration still not applied but may be deprioritized given Augie's shift in focus.
AI-019 | Grant Ajer and Liam access to the ThoughtSpot FlexPoint organization environment so they can visualize model outputs directly in ThoughtSpot instead of via Excel/Python charts. | Augie / Mariana | Completed | Call 2 – Feb 18, 2026 | Call 7 – Apr 8, 2026 | Resolved live during Call 7. Mariana confirmed: 'I'll send you Azure and Liam an email — just log in, create a new password, and you should have access.' Augie escalated this as top priority at call start. Access granted during the call.
AI-020 | Once model is refined, build pipeline to push daily scoring output directly into the database so ThoughtSpot can auto-refresh projections without manual intervention. | Ajer / Liam + Mariana/Israel | In Progress | Call 2 – Feb 18, 2026 | Call 7 – Apr 8, 2026 | With Gallows access granted, team can now build directly in Gallows environment. No reason to build outside it. DB connection to follow once dashboard is polished.
AI-021 | Add footnotes to all presentation slides: data sample size, time frame used, methodology summary. Standard for any client-facing analytical output. | Ajer / Liam | Completed | Call 2 – Feb 18, 2026 | Call 3 – Feb 25, 2026 | Team confirmed they will add footnotes. 15,000+ loans referenced in Call 3 presentation. Sample sizes and methodology mentioned verbally. Implemented going forward.
AI-022 | Fix chart color scheme in model output slides — numbers were hard to read due to poor contrast. Use black text. | Ajer / Liam | Completed | Call 2 – Feb 18, 2026 | Call 3 – Feb 25, 2026 | Not explicitly flagged as an issue in Call 3. Assumed fixed.
AI-023 | Explore integrating model projections with the corporate P&L and balance sheet model to produce projected revenue, expenses, profit and balance sheet items by division. | Augie / Mariana / Ajer / Liam | In Progress | Call 2 – Feb 18, 2026 | Call 4 – Mar 4, 2026 | Augie reframed: primary value is now operational (which loans to prioritize) not just P&L forecasting. CFO meeting will help define exact deliverable. Still on roadmap.
AI-024 | Build 'loan elimination' rules: identify combinations of variables that predict non-funding with 90%+ confidence (e.g. stuck in underwriting + lock expiring + low credit score). Flag/discard these loans from projections. | Ajer / Liam | Completed | Call 3 – Feb 25, 2026 | Call 4 – Mar 4, 2026 | Pipeline hygiene filter built. 46% of active pipeline flagged as dead weight. Zero false negatives across 128 backtest snapshots. Rules: (1) opened 30+ days=0.006% funding, (2) submitted+unlocked 22+ days=0.1%, (3) approved+expired lock=0%. Error tightens to 4.7% with filter on.
AI-025 | Build interaction features combining lock expiry proximity + days at current stage (e.g. approved for 45 days + lock expiring in 2 days = high drop-off signal). Model these in combination, not just independently. | Ajer / Liam | Completed | Call 3 – Feb 25, 2026 | Call 4 – Mar 4, 2026 | 12 interaction features built (lock×stage, lock×time, pipeline velocity, lock extension proxies). Top 3: approved-to-lock speed (#8), locked-at-early-stage (#11), stages-per-day (#14). MAPE unchanged at 4.8% — GBM already discovering combinations internally. Features improve transparency/auditability.
AI-026 | Build timing prediction: predict WHEN each loan will fund (day of month), not just IF it will fund. Analyze average time between each pipeline stage (e.g. funding conditions → funded, docs → funding). | Ajer / Liam | Completed | Call 3 – Feb 25, 2026 | Call 4 – Mar 4, 2026 | Weekly timing model built. 38% of volume lands in last week (structural backloading). Week 1=18%, Week 2=21%, Week 3=23%, Week 4=38%. GBM regressor: 2.8 days MAE per loan. Recommendation: use historical distribution at day 0, GBM takes over from day 8.
AI-027 | Run model on current February and March pipelines and send Augie the live projected funding amounts for both months. | Ajer / Liam | Completed | Call 3 – Feb 25, 2026 | Call 4 – Mar 4, 2026 | Implied resolved — team presented live V3 model in Call 4. No explicit mention of Feb/Mar output being sent separately, but model is operational.
AI-028 | Reduce model error from 4.8% toward 2-3% through further variable refinement, interaction features, and elimination rules. | Ajer / Liam | In Progress | Call 3 – Feb 25, 2026 | Call 4 – Mar 4, 2026 | Augie revised view in Call 4: 'I can live with 4.8%. Getting to 2% isn't going to be revolutionary.' Focus has shifted from error reduction to actionable outputs (pipeline hygiene, timing, kill zone). Still a long-term goal but no longer the primary focus.
AI-029 | Send Call 3 recording and slide deck to Augie immediately after the call. | Mariana | Completed | Call 3 – Feb 25, 2026 | Call 4 – Mar 4, 2026 | Team sent deck to Augie's email during Call 3. Recording assumed sent. No issues raised in Call 4.
AI-030 | Augie to send summary feedback points / additional direction to team after reviewing the Call 3 recording. | Augie | Completed | Call 3 – Feb 25, 2026 | Call 4 – Mar 4, 2026 | Augie provided extensive direction during Call 4 on pipeline hygiene business value, CFO presentation, LinkedIn podcast, and operational dashboard vision.
AI-031 | Present model and findings to the CFO of the client company (FlexPoint). Prepare a client-facing presentation showing pipeline hygiene, kill zone analysis, timing model, and operational recommendations. | Ajer / Liam (+ Augie arranging) | In Progress | Call 4 – Mar 4, 2026 | Call 7 – Apr 8, 2026 | No CFO meeting date set. Focus is on perfecting the dashboard first. Augie wants actionable insights + agent built before presenting to CFO. Summer timeline constraint emerging — interns leave June.
AI-032 | Build an operational loan prioritization report/dashboard: tier active loans into (1) Dead — drop immediately, (2) Watch — low probability but alive, (3) Push — high probability, late stage, get docs in. | Ajer / Liam | Completed | Call 4 – Mar 4, 2026 | Call 6 – Apr 1, 2026 | V1 of operational dashboard delivered in Call 6 with 4 tabs. Augie: 'Really good start.' Now entering iteration/elevation phase with Claude. Next: improve visual design, add sizzle, refine watchlist logic.
AI-033 | Develop creative terminology and branding for model outputs: 'Pipeline Hygiene', 'Kill Zone', loan buckets, etc. Make visualizations rich and client-presentable using ThoughtSpot/Gallows graph library. | Ajer / Liam + Augie | In Progress | Call 4 – Mar 4, 2026 | Call 7 – Apr 8, 2026 | New terminology added: 'Revenue at Risk', 'Recovery Opportunities', 'What-If Levers', 'Pipeline Health', 'Scorecards'. Four operational levers quantified. Balanced Scorecard concept introduced. Ongoing.
AI-034 | Produce a LinkedIn podcast / article about the UChicago × Gallows collaboration. Use proxy names (e.g. 'Falcon' instead of FlexPoint). Publish to LinkedIn to generate visibility for all parties. | Augie + Ajer / Liam | In Progress | Call 4 – Mar 4, 2026 | Call 5 – Mar 25, 2026 | Not discussed directly. Still on roadmap. No timeline set.
AI-035 | Obtain lock extension / relock history data from FlexPoint to improve the elimination filter and timing model. Currently proxied by checking if loan is alive past lock expiry. | Mariana / Israel (request to FlexPoint) | Pending | Call 4 – Mar 4, 2026 | Call 5 – Mar 25, 2026 | Not discussed in Call 5. Still awaiting FlexPoint data. No update.
AI-036 | Define and implement reporting cadence recommendation: day-0 directional read, day-8 report (model under 10% error), day-15 precise report (4.8% error). Propose this schedule to client. | Ajer / Liam | In Progress | Call 4 – Mar 4, 2026 | Call 5 – Mar 25, 2026 | Concept discussed (ops manager opens dashboard Monday morning). Cadence not yet formalized. Will be defined once mock dashboard is built.
AI-037 | Send Call 4 slide deck / presentation to team after the call. | Ajer / Liam | Completed | Call 4 – Mar 4, 2026 | Call 5 – Mar 25, 2026 | No issues raised. Assumed completed after Call 4.
AI-038 | Build a mock dashboard / mock product prototype showing: loan prioritization tiers (Dead/Watch/Push), pull-through rates by product, cycle time distributions, and broker quality scores. Use as basis for CFO presentation and Gallows integration. | Ajer / Liam | Completed | Call 5 – Mar 25, 2026 | Call 6 – Apr 1, 2026 | Mock dashboard LIVE and presented in Call 6. 4 tabs: (1) Overview — $314M total pipeline, $167M dead, $147M live, $100M projected to fund April, 5.8% error; (2) Watchlist — 59 at-risk loans with personalized reasons per loan; (3) Live Pipeline ranked by expected value (probability × loan amount); (4) Trends — pull-through rates by month + cycle times (median 29 days). Built using Claude. Color issue noted (gray/blue mix-up) — to fix.
AI-039 | Analyze pull-through rates by product (conventional, FHA, VA, non-QM, HELOC) and cycle times (application-to-funding) to establish baseline diagnostics. Identify high-variance products and SLA breakers. | Ajer / Liam | Completed | Call 5 – Mar 25, 2026 | Call 6 – Apr 1, 2026 | Pull-through rate trend and cycle time distribution both live in dashboard. Median cycle time = 29 days. Month-by-month pull-through trend shown. Partial data visible for current month. Augie validated both as key metrics.
AI-040 | Design and build a 'Broker Quality Score' metric: rank brokers by loan quality (FICO scores, exception rates, pull-through rates, cycle times, margin per loan). Flag high-volume but low-quality broker relationships. | Ajer / Liam | In Progress | Call 5 – Mar 25, 2026 | Call 7 – Apr 8, 2026 | Not yet built. Augie: 'Clients want to know which brokers are sending quality loans.' Scorecard tab addresses product/channel performance but broker-level scoring not yet added.
AI-041 | Quantify the ROI of loan prioritization for the CFO pitch: calculate revenue impact of 1% pull-through rate improvement ($400K per $1B in volume at ~400bps margin). Build a client-facing ROI calculator. | Ajer / Liam | In Progress | Call 5 – Mar 25, 2026 | Call 6 – Apr 1, 2026 | Not yet built as standalone tool. Augie re-stated the $13K/loan revenue point live: 'Every loan that doesn't fund = $13K lost.' Value framing confirmed. Full ROI calculator still needed for CFO pitch.
AI-042 | Define the primary end-user of the operational tool as the Ops Manager (not the capital markets desk). Design the dashboard UX around their Monday-morning workflow: ranked loan list, tier labels, action recommendations. | Ajer / Liam | Completed | Call 5 – Mar 25, 2026 | Call 6 – Apr 1, 2026 | Dashboard designed around ops manager workflow. Watchlist = 59 loans needing attention with per-loan specific reasons. Live pipeline = ranked by expected value. Eliminated tab = dead loans to ignore. High-level-to-detail flow confirmed by Augie.
AI-043 | Analyze the virtuous cycle of speed improvement for broker retention: faster cycle times → better broker experience → broker sends more loans → higher volume. Quantify and include in CFO pitch. | Ajer / Liam | In Progress | Call 5 – Mar 25, 2026 | Call 6 – Apr 1, 2026 | Augie re-emphasized $13K per unfunded loan and importance of cycle times for broker retention. Not yet formalized as a deliverable. Tied to CFO pitch.
AI-044 | Schedule a Claude AI working session with Augie, Ajer, Liam, and Mariana early next week (week of Mar 30) to use Claude for business strategy, metric definition, and product positioning. | Ajer / Liam (via Slack to Mariana) | In Progress | Call 5 – Mar 25, 2026 | Call 7 – Apr 8, 2026 | Not yet held as a formal session. Discussed extensively in Call 7. Augie will provide enterprise Claude account access + Gallows email. Ajer to set up shared project after receiving credentials. Target: before summer internships start (June).
AI-045 | Reschedule weekly meeting to 3:30 PM Wednesday (or another early afternoon slot) to accommodate Ajer's new class schedule. Confirm via Slack. | Ajer (via Slack to Mariana) | Completed | Call 5 – Mar 25, 2026 | Call 7 – Apr 8, 2026 | Call 7 held as normal Monday session. Cadence appears resolved informally.
AI-046 | Fix dashboard color coding issue: gray = total pipeline, blue = live pipeline. Colors got mixed up when changing themes. Must be corrected before any client-facing use. | Ajer / Liam | In Progress | Call 6 – Apr 1, 2026 | Call 7 – Apr 8, 2026 | Not explicitly addressed in Call 7. Dashboard V2 presented with multiple new tabs. Assumed still pending unless fixed during build.
AI-047 | Investigate data quality issue: one conforming loan appears on the watchlist as unlocked (no rate lock) at CTC stage. Likely mislabeled — Fannie/Freddie conforming loans at CTC are always locked. Could be a non-QM loan labeled incorrectly as conforming. | Ajer / Liam + Mariana / Israel | In Progress | Call 6 – Apr 1, 2026 | Call 7 – Apr 8, 2026 | Not explicitly resolved in Call 7. Augie did not raise it again. Likely being addressed as part of dashboard iteration.
AI-048 | Add 'loss analysis' tab to the dashboard: document eliminated loans that unexpectedly did NOT fund, and flag any loans that were eliminated by model but should have been pursued. Support root cause analysis on lost revenue. | Ajer / Liam | In Progress | Call 6 – Apr 1, 2026 | Call 7 – Apr 8, 2026 | Not yet built as a standalone tab. The 'What-If' tab and Recovery Opportunities table partially addresses this. Full loss analysis still pending.
AI-049 | Set up a shared Claude project workspace for the full team (Augie, Ajer, Liam, Mariana). Ajer to send Augie instructions for adding shared project members. Mariana to confirm the shared button setup. | Ajer (instructions to Augie) + Mariana (admin setup) | Completed | Call 6 – Apr 1, 2026 | Call 7 – Apr 8, 2026 | Resolved during Call 7. Augie: 'I'll give you guys a Gallows email and access to our enterprise account so you can work under a common workflow.' Mariana also resolved ThoughtSpot access. Both shared access items unblocked.
AI-050 | Elevate dashboard from 'solid start' to 'brilliant analytical output': improve visual layout (headline KPIs at top → distribution → detail), add design polish, ensure information hierarchy follows high-level-to-detail flow. Use Claude for iteration. | Ajer / Liam (with Claude) | In Progress | Call 6 – Apr 1, 2026 | Call 7 – Apr 8, 2026 | Major progress in Call 7 — V2 dashboard presented with 6 new tabs. Augie gave detailed feedback: add variance metrics (IQR/std dev), add product-level benchmarks, build balanced scorecard composite KPI, add action recommendations per loan. Still iterating.
AI-051 | Transfer finalized dashboard from Claude/sandbox environment to Gallows front-end platform for production use by client ops teams. | Mariana / Israel + Ajer / Liam | In Progress | Call 6 – Apr 1, 2026 | Call 7 – Apr 8, 2026 | Access granted during Call 7. Team can now build directly within Gallows environment. No reason to build outside it going forward per Augie. Transfer begins next iteration.
AI-052 | Add per-loan action recommendations to the Watchlist and Live Pipeline tabs: for each at-risk or low-probability loan, show specific actions that would increase its funding probability and by how much (e.g. 'Get W-2 income verification → probability increases from 16% to 30%'). | Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'How cool would it be if we say — take this action and you increase the probability from 16% to 30%?' Ajer confirmed: 'We'll definitely make that change.' This is the key bridge between diagnosis and prescription.
AI-053 | Build a 2×2 bubble chart matrix: Y-axis = probability of funding (or expected value), X-axis = difficulty to execute (number of remaining hurdles/actions), bubble size = loan amount. Highlight quick-win quadrant (upper-left: high probability + low effort). | Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'I want to tackle the upper-left — high probability of funding with least work involved. Highlight those that with a simple action can move from bottom-left to upper-left.' Moneyball analogy: pick up the chips that give you the highest probability with least effort.
AI-054 | Add variance metrics to Pipeline Health tab: replace or supplement medians with IQR (interquartile range), box plots, or min/max/Q1/Q3. Apply to stage transition times AND conversion rates, broken down by product. | Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'I caution folks on medians — you can have a good median but a big variance, meaning you're providing a shitty service to 20% of customers.' Domino's analogy: median 18-min delivery means nothing if 20% wait 50 min. Goal: competitive medians AND low variance.
AI-055 | Research and add product-level industry benchmark cycle times. Flag whether a VA loan taking 20 days at approved-to-CTC is above or below industry standard for that product type. | Ajer / Liam (use Claude/AI for research) | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'VA at 20 days might not be a bad thing — VA is a more complicated loan than FHA.' Need product-specific benchmarks to contextualize cycle times. Augie suggested using Claude/ChatGPT to source industry standards.
AI-056 | Build a Balanced Scorecard composite KPI for each product type: agree on the KPIs (pull-through rate, cycle time, average loan size, volume, revenue efficiency), assign weights, compute a single composite score. Track over time. | Ajer / Liam + Augie (weight definition) | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'Create a balanced scorecard — a number that is the balanced result of all these KPIs. Then I can say conforming is at a 7, typically trending 7.7 — what happened?' Example: non-conforming scored highest on pull-through (40%) + highest loan size + highest efficiency. Composite score enables simple client-facing health check.
AI-057 | Red-team all model conclusions and dashboard recommendations using AI (Claude or ChatGPT): prompt it to act as an operations expert for an independent mortgage bank and challenge every conclusion with industry knowledge. | Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'Red team the hell out of them. The CIA has teams whose job is just to disprove conclusions — so we don't bomb the wrong house.' Use AI to stress test before presenting to CFO. Liam: 'We could even have an API call that red-teams in real time within the dashboard.' This is the final validation step before client delivery.
AI-058 | Build a Claude AI agent (using Anthropic API key from Gallows enterprise account) that autonomously analyzes mortgage pipeline data, generates actionable operational insights, and recommends resource reallocation. Use sub-agent architecture to avoid hallucination. | Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'Before you guys go for summer, let's create an agent working 24/7 for us.' Goal: full automated diagnosis of mortgage ops health → actionable insights. Liam explained API key mechanics. Augie: use sub-agents (silo processes, pass output to next agent) to reduce hallucination risk. Anthropic enterprise API key = Gallows account.
AI-059 | Recommend 2–3 high-quality UChicago interns (from UMAG club or personal network) to Augie for summer. Augie wants serious candidates who can continue the work Ajer and Liam have done. | Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'I want people you think will be serious and can actually continue the good work.' He can get university funding for interns. Both Ajer and Liam confirmed they are in UMAG. Need to provide names before summer.
AI-060 | Plan timeline and deliverables for remaining weeks before summer internships start (late May). Ajer and Liam start internships in June with only 3 days gap after UChicago ends. Prioritize agent build and dashboard finalization. | Augie + Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'Let's be respectful of your timeline.' Ajer and Liam: 'UChicago ends late May — only 3 days before internship starts.' Finite window remaining. Key deliverables to complete: agent build, balanced scorecard, dashboard polish, Gallows transfer, red-team validation.
AI-061 | Mariana to review all prior call recordings/notes and compile a master priority list and task hierarchy document with Augie. Share with Ajer and Liam as the official project to-do tracker. | Mariana + Augie | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie: 'Mariana, let's review the document tomorrow based on all the calls — create a list of priorities and hierarchy.' He also wants all to-dos not to get lost in weekly shuffles. This is essentially a request for the tracker document (this file).
AI-062 | Tennis + dinner meetup: Augie to play tennis with Ajer on Monday Apr 13 at 8am, followed by dinner at the Quadrangle Club (6–7pm), then EBC. Liam invited for dinner. | Augie (arrange) / Ajer / Liam | New | Call 7 – Apr 8, 2026 | Call 7 – Apr 8, 2026 | Augie proposed at end of call. Social/relationship building. Ajer confirmed. Liam invited for dinner portion (Augie unsure about Liam's tennis level — joke made). Informal project review may happen during dinner.

## Questions & Clarifications
QUESTIONS & CLARIFICATIONS TRACKER
Question ID | Question | Raised By | Status | Answer / Resolution | Notes
Q-001 | How much freedom do we have to customize or replace the existing model vs. just adding more variables to it? | Ajer | Answered | Full freedom granted. Augie said: 'If you say this is not working, delete everything and start from zero.' The goal is a more accurate model, regardless of the approach. | Augie explicitly gave carte blanche to redesign the model if needed.
Q-002 | What exactly are we trying to predict — number of loans funded, dollar volume, or a specific milestone? | Ajer | Answered | Dollar volume of loans reaching the 'Funded' stage. Current output: total projected monthly fundings split by retail and wholesale (e.g., $118M for Feb, of which $38.6M already funded). | ThoughtSpot dashboard shown live. Forecast = remainder of month only, not full month from day 1.
Q-003 | Should we focus on the most explanatory variables or try to build a model that accommodates as many inputs as possible? | Ajer | Answered | Focus on the most influential variables only. Augie: 'I don't want to add too many variables because too many can add noise.' Prioritize variables with highest correlation to funding outcome. | Augie used dunking analogy: height and basketball experience matter; food preferences don't.
Q-004 | How much of a 'paper trail' or explanatory documentation do we need to produce alongside the model outputs? | Liam | Answered | Augie confirmed: focus first on model accuracy. Variable weights/coefficients will be documented for clients once model is stable. Presentation quality (footnotes, sample sizes) is expected. | Augie acknowledged it will eventually be needed to explain model to clients, but not the immediate priority.
Q-005 | Can Augie join the weekly Wednesday calls given his awareness of the model background? | Ajer | Answered | Yes. Augie joined this call mid-way and agreed to the weekly Wednesday cadence. | Team open to shifting time if Augie's schedule requires it.
Q-006 | What are the current two variables being used in the predictive model? | Ajer | Answered | Three variables confirmed: (1) Loan amount, (2) Channel (retail vs. wholesale), (3) Loan type. Time windows also used: 28, 30, 31 days. | Clarified during the first portion of the call by Speaker 1 / Mariana.
Q-007 | Should exogenous variables like interest rates be incorporated into the model? | Augie (raised proactively) | Answered | Not at this stage. Augie: 'I don't want to introduce exogenous factors just yet.' Focus on internal pipeline variables and loan characteristics first. | Augie acknowledged rate volatility has real impact (e.g., rate drops cause delays as borrowers renegotiate), but deferred to future phase.
Q-008 | Why does 'product' not appear as an independent variable in the feature importance chart if it was shown to have significant impact in the previous slide? | Augie | Answered | Product and purpose are embedded inside the pipeline stage probability feature (the 59.5% driver). They don't appear separately because their signal is baked into that combined feature. Augie flagged this needs to be decoupled for cleaner client reporting. | This led to AI-015 — team must isolate each variable's independent contribution.
Q-009 | Is 'rate lock' a real leading indicator of funding, or is it just a process milestone that correlates because locked loans are already far along? | Ajer / Liam | Answered | Augie explained: rate lock = contractual agreement between lender and borrower to fix the rate. A loan that never locks is not serious — 'mortgage banking doesn't work without locking the rate.' Lock date and lock expiration date are both strong predictors. Lock expiration proximity adds urgency. | Team found locked loans fund 79% vs <1% unlocked. Augie confirmed it is a genuine leading indicator AND a capital markets mechanism separate from the pipeline milestones.
Q-010 | Should the back-test use a mid-month pipeline snapshot or end-of-prior-month snapshot for projecting each month? | Augie | Partially Answered | Rolling window was the main fix: Nov error 28%→13%, Dec 15%→6%. Root cause still not fully explained. Lock features had less impact on these months than expected. Seasonality hypothesis not yet tested as fix. | Critical methodology fix — flagged as AI-013.
Q-011 | What caused the November and December 2025 outlier errors (28% and 16% over-projection)? | Ajer / Liam | Answered | Tested in Call 3. Summer pull-through=41% vs winter=36%. Volume 25% higher in summer. KEY FINDING: days-to-fund is flat year-round. Conversion rate shifts, not speed. Can be added as optional feature. | Flagged as AI-014. High priority.
Q-012 | Should seasonality (month of year, summer vs winter) be added as an independent variable in the model? | Augie (proactively) | Answered | Augie's gut: summer months are more competitive → faster closings. But he flagged it as a hypothesis, not confirmed. Team should test it empirically. | Flagged as AI-017.
Q-013 | When should the model be connected to the database for daily automated scoring vs. manual runs? | Ajer / Liam | Answered | Sequenced by Augie: (1) refine model first, (2) then pipe output to DB for daily auto-scoring, (3) then ThoughtSpot visualizes it. Do not build the pipeline before the model is stable. | Flagged as AI-020.
Q-014 | Is rate lock an independent signal or does it just re-encode what the pipeline stage already tells us? Should Version A (no lock) or Version B (with lock) be used? | Ajer / Liam | Answered | Augie: 'Version A shouldn't exist. We have to use the lock information — it would be silly not to.' Lock is a fundamental part of the mortgage process. No mortgage banking without locking. Version B confirmed. Lock + lock expiry are essential features. | Resolves the A vs B question. Team's concern about multicollinearity acknowledged but overruled by business logic. AI-016 confirmed complete.
Q-015 | How should lock data be combined with pipeline stage data to maximize predictive power rather than treating them as independent variables? | Augie | Answered | Built and validated in Call 4. 38% of volume in last week (structural). Weekly distribution: 18/21/23/38%. GBM: 2.8 days MAE per loan. Historical pattern best at day 0; GBM takes over from day 8. Confirmed backloading is structural — end-of-month push confirmed. | Led to AI-024 (elimination rules) and AI-025 (interaction features).
Q-016 | Can the model predict WHEN a loan will fund (specific day/week of month), not just IF it will fund and total monthly volume? | Augie | Answered | V3 model presented as operational in Call 4. Team confirmed live scoring capability. Specific Feb/Mar numbers not shared publicly in transcript but model confirmed ready. | Critical for client liquidity planning. Led to AI-026.
Q-017 | What is the current February projection and March projection from the live model? | Augie | Unanswered | Not run during the call. Team said it needs ~10 minutes. Agreed to send output after the call. Augie noted: for Feb, only tomorrow and Friday remain to predict since days 1-24 are already observed. | AI-027 assigned.
Q-018 | Is 4.8% MAPE measured at mid-month (day 15) or at day zero (before month starts)? | Augie | Answered | Augie clarified his own confusion: 4.8% is the mid-month number (day 15). Day-zero error is ~17%. Augie confirmed: 'I can live with 4.8% as long as it's before the month begins for day-zero reads' — though technically day-zero is 17%. MAPE calculated on trailing 12 months. | Important distinction for client reporting. Day-0=17%, Day-8=<10%, Day-15=4.8%, Day-22=4.0%.
Q-019 | What is the business value of pipeline hygiene / loan elimination beyond just improving forecast accuracy? | Augie (raised proactively) | Answered | Augie: Eliminate dead loans → clients reallocate ops team effort → more loans processed with same headcount → higher pull-through rates → more revenue. Also: replace first-in-first-out queue with probability-ranked pipeline. Core business value = efficiency + cost reduction. | This reframed the project's value proposition. Model is not just a forecasting tool — it's an ops efficiency tool. Led to AI-032 (operational dashboard).
Q-020 | What are the distinct archetypes of loans that fail, and how early in the pipeline do most failures occur? | Team (presented) | Answered | 5 archetypes from 9,611 failed loans: (1) Early dropouts=44.6% — gone in 4 days, rate shoppers/incomplete; (2) Pre-approval stall=7.6% — stalls before approval; (3) Approved+never locked=7.6% — sits 75 days median then dies; (4) Lock expired=3.4% — locked, ran out, never returned; (5) Late-stage surprise=1.5% — made it far but something went wrong (appraisal etc). 94% of failures never get past approved = the Kill Zone. | Augie loved 'Kill Zone' as new terminology. This analysis gives clients a diagnostic tool, not just a forecast.
Q-021 | Should the project now shift from model improvement to productization / operational tool building? | Augie (direction given) | Answered | Yes. Augie: 'Let's transition — I'm okay living with 4.8%. Let's think about what other metrics and terms we can come up with. Let's make it usable.' Getting from 4.8% to 2% is not revolutionary. The bigger value is the operational dashboard, CFO presentation, and packaging. | Major strategic pivot in Call 4. Shifts from 'build better model' to 'package and deliver value to client.' Led to AI-031–AI-034.
Q-022 | Does telling the ops team to drop dead loans (based on model recommendation) create a self-fulfilling prophecy that corrupts future model training data? | Liam | Answered | Augie and Liam discussed. Solution: flag loans as 'dropped per model recommendation' separately from 'pursued but failed to fund' in the dataset. This allows the model to distinguish model-influenced outcomes from natural failures when retraining. Tracking ops team actions is required. | Important model governance issue. Needs to be built into the data pipeline. Liam identified this unprompted — Augie praised the insight.
Q-023 | What is the exact ROI metric to present to the CFO — what number will resonate most? | Ajer | Answered | Pull-through rate improvement is the primary KPI. Formula: $1B volume × 1% pull-through improvement = $10M extra volume × ~400bps margin = ~$400K additional revenue. Each funded loan = ~$13K revenue. Secondary: lower cycle times → broker retention → more loan volume (virtuous cycle). | Augie calculated this live. CFO pitch should lead with the pull-through rate % and translate it directly to dollars.
Q-024 | Who is the primary end-user of the operational tool — capital markets desk or ops manager? | Ajer | Answered | Ops Manager. Their job = process loans as fast as possible. They open the dashboard Monday morning and need a ranked, actionable list. Capital markets desk cares about monthly forecast numbers (different product). | Key UX design decision. Two different products for two different users. For now, focus on ops manager.
Q-025 | Why is there such significant variance in loan profitability (basis points) within the same product type? | Augie (raised proactively) | Unanswered | Not resolved. Augie showed live data: non-QM ranged from 240 to 518 basis points on the same product. Hypothesis: cycle time differences, broker relationships, rate lock timing. Augie: 'We need to get a crisp diagnosis first.' Requires further analysis. | This is a new analytical thread beyond funding prediction. Links to cycle time analysis (AI-039) and broker quality scoring (AI-040).
Q-026 | Are clients (FlexPoint and others) currently tracking broker quality or loan prioritization metrics in any systematic way? | Team + Augie | Answered | No. Augie: 'They have no idea. It's all gut feel.' Clients are only asking for basic rankings (e.g. which underwriter closed more loans). No probability-based prioritization, no broker quality scoring, no SLA variance tracking. Augie: 'I don't even know why this hasn't been solved yet.' | Confirms massive white space opportunity. Augie compared to Moneyball — data-driven decision making in a gut-feel industry.
Q-027 | How does faster cycle time create a competitive advantage in the wholesale mortgage business? | Team (discussed) | Answered | Brokers shop across multiple wholesale lenders simultaneously. They send future loans to whichever lender funds fastest. Speed = differentiation (price is commoditized). Faster cycle times → broker loyalty → more loan flow → more revenue. Virtuous cycle confirmed by Augie. | This is the second revenue lever after pull-through rate improvement. Should be included in CFO pitch (AI-041, AI-043).
Q-028 | What is the definition of 'live pipeline' shown in the dashboard overview? | Augie | Answered | Loans still active that have NOT been eliminated by the hygiene filter. Total active pipeline = $314M. Of that, $167M is flagged as dead/rotten. $147M is live. Of the $147M live, $100M is projected to fund in April at 5.8% error. | Augie confirmed he understood the definition after Ajer explained. Dashboard overview tab confirmed as correct.
Q-029 | What should happen to the 'Eliminated' loans tab — is it just a graveyard or should it serve a purpose? | Augie (raised proactively) | Answered | Should serve an active purpose: document WHY each loan was eliminated, flag any that unexpectedly did fund (false positives), and identify patterns in lost revenue. Augie: 'I want less spoiled milk going forward — document the ones that shouldn't have been eliminated.' Ties to AI-048 and the self-fulfilling prophecy risk (AI-027). | Eliminated tab should become a learning/QA tool, not just a disposal bin.
Q-030 | How should the team collaborate on Claude — shared account, individual accounts, or a team project? | Ajer | Answered | Best approach: one shared Claude Team account with a project folder (e.g. 'UChicago FlexPoint Dashboard'). All model code, dashboard code, and chat history live in that shared project context. All team members added as collaborators. Ajer to send Augie setup instructions. Mariana already has shared button but needs review. | Augie confirmed he wants a common workflow. Everyone at Gallows has a Claude license but shared project workflow not yet set up. Target: resolve before the Claude working session.
Q-031 | Is the conforming loan showing as unlocked at CTC stage (#9 on watchlist) a real edge case or a data labeling error? | Augie | Unanswered | Flagged but not resolved. Augie: 'I don't see a Fannie Mae or Freddie Mac loan at CTC that hasn't been locked.' Most likely a non-QM loan mislabeled as conforming. Requires data QA by Mariana/Israel. | AI-047 assigned. Must be resolved before client-facing demo — a data error on the watchlist would undermine credibility.
Q-032 | Why haven't Ajer and Liam been given ThoughtSpot/Gallows access yet, despite it being discussed since Call 2? | Augie | Answered | Oversight by internal team. Augie: 'There's no reason Ajer and Liam should be building anything outside of ThoughtSpot.' Mariana resolved live during Call 7 — sent email with login credentials. Also Gallows enterprise Claude access to be granted by Augie. | Resolved during Call 7. Augie made it top priority at call start. AI-019 marked Completed.
Q-033 | What is the exact structure and quantified upside of the four operational levers identified in the What-If tab? | Team (presented) | Answered | 4 levers with calculated dollar impact: (1) Improve rate lock at approved: 292 unlocked loans, 7% avg prob vs 61% when locked — 40% lock rate = ~$22M upside; (2) Accelerate approved-to-CTC: reducing cycle time at the bottleneck = ~$98M; (3) Reactivate stale pipeline: 178 loans stalled 30+ days — targeted re-engagement = ~$5.8M; (4) Retail channel optimization: retail=5% pull-through vs wholesale=30%, closing half the gap = ~$700K. Total potential = ~$40M = 127% above current projection. | These are the headline CFO numbers. Augie: 'Even 20-30% of that would be a big bonus.' Stress testing with industry knowledge still needed.
Q-034 | What is the risk of presenting data-driven conclusions without industry knowledge validation? | Augie | Answered | Augie: 'The art mixes with the science.' Data conclusions must be stress-tested against industry expertise before presenting to clients. Risk: a conclusion may be directionally correct in data but incorrect operationally. Solution: red-team all conclusions using AI acting as an ops expert for an independent mortgage bank. Build red-teaming into the workflow (AI-057). | Augie used tennis serve analogy: high serve speed correlates with winning points but also with more double faults. Data alone doesn't capture all trade-offs.
Q-035 | What is the vision for the Claude agent, and what architecture should be used? | Augie + Liam | Answered | Vision: a 24/7 agent that autonomously analyzes mortgage pipeline data, identifies operational inefficiencies, and recommends actionable resource reallocation decisions. Architecture: sub-agents (siloed processes that pass output to next agent) to reduce hallucination risk. API key from Gallows Anthropic enterprise account. Liam: 'Embed instructions in code, call Anthropic's engine.' Augie: 'Sub-agents are the right approach.' | This is the final, most ambitious deliverable before summer. AI-058. Augie: 'I'd love this to be my first agent.' Liam suggested potential for real-time red-teaming API call within the dashboard.
Q-036 | How much time do Ajer and Liam have left before their summer internships begin? | Augie | Answered | UChicago ends late May. Both Ajer and Liam start their internships in June with only ~3 days between end of school and start of work. Effectively 6-7 weeks of project time remaining from April 8. Augie: 'I want to be respectful of your timeline.' | Critical for project planning. Key deliverables must be scoped and prioritized for the remaining window. AI-060 assigned.

## Decisions
DECISIONS LOG
Decision ID | Decision | Made By | Context / Rationale | Date
D-001 | Weekly Wednesday calls established as the recurring cadence for project check-ins | Augie, Ajer, Mariana | All parties agreed. Ajer/Liam confirmed Wednesday works; team is open to adjusting time if needed for Augie. | Apr 14, 2026
D-002 | Team is free to redesign the model from scratch if the existing approach is insufficient | Augie | Augie explicitly said: 'If you say this is not working, delete everything and start from zero.' No constraints placed on the technical approach. | Apr 14, 2026
D-003 | First priority enhancement: add 'product' and 'purpose' as new predictive variables | Augie | Augie stated he guarantees these will add significant predictive value. Product = Fannie/Freddie vs. Government. Purpose = Purchase vs. Refi. These are the first variables to test. | Apr 14, 2026
D-004 | Model will focus only on the most explanatory variables; will NOT incorporate exogenous factors (e.g. interest rates) at this stage | Augie | Augie: too many variables introduce noise. External macro factors deferred to a future phase. | Apr 14, 2026
D-005 | Python is the primary development language for modeling and analysis | Ajer / Liam | Ajer confirmed Python is the team's most comfortable language. No objection raised by Mariana/Israel. | Apr 14, 2026
D-006 | Slack forecasting channel to be used as async communication hub between calls | Mariana / Israel | Israel already added. Liam to be added. Any questions, doubts, or updates go to the channel. | Apr 14, 2026
D-007 | Back-testing approach confirmed: use historical data to predict a known period and compare vs. actuals | Augie | Augie described this as an 'open book test' since outcomes are already known. Recommended predicting last quarter of prior year. | Apr 14, 2026
D-008 | Run 3–5 different model methodologies in parallel and select best based on predictive accuracy | Augie | Augie instructed team not to commit to one model. Run multiple and compare performance. | Apr 14, 2026
D-009 | Back-test methodology must use end-of-prior-month pipeline snapshot (not mid-month or any other date) | Augie | Using incorrect snapshot date inflates accuracy artificially. Standard: Oct 31 for Nov projection, Nov 30 for Dec projection. | Feb 18, 2026
D-010 | Rate lock date and lock expiration date must be incorporated as model variables | Augie | Augie guaranteed these will have significant explanatory power. Lock is a capital markets signal independent from pipeline milestones. | Feb 18, 2026
D-011 | Sequencing confirmed: (1) Refine model → (2) Pipe output to database → (3) ThoughtSpot visualization. Do not skip steps. | Augie | Augie explicit: 'The first step is tweaking the model. Then figure out a way to bring projections into the DB so we can graph it.' | Feb 18, 2026
D-012 | ThoughtSpot access (FlexPoint org) to be granted to Ajer and Liam for visualization and experimentation | Augie | Augie committed to providing access. Mariana to coordinate internally. | Feb 18, 2026
D-013 | Product and purpose variables must be decoupled from pipeline stage feature to show independent explanatory power | Augie | Current architecture embeds product/purpose inside pipeline stage probability. Augie: clients will want to see each variable's own coefficient (econometrics standard). | Feb 18, 2026
D-014 | Presentation standard established: all slides must include footnotes with sample size, time frame, and methodology | Augie | Client-facing standard. Augie: 'Otherwise people are asking where's the time frame, where's the data?' Applies to all future presentations. | Feb 18, 2026
D-015 | Version B (with rate lock features) is the chosen model path. Version A (without lock) is rejected. | Augie | Augie: 'Version A shouldn't exist. It would be silly not to use lock data.' Lock is a fundamental mortgage banking data point. Decision is final. | Feb 25, 2026
D-016 | Next development priority is timing prediction (WHEN loans fund), not further accuracy improvement on IF they fund. | Augie | Augie: 'The when is crucial — clients need to plan liquidity.' End-of-month funding spikes confirmed in ThoughtSpot. Team to build day-of-month prediction. P&L integration depends on this. | Feb 25, 2026
D-017 | Loan elimination rules must be built: model must be able to confidently discard loans that will NOT fund, not just predict those that will. | Augie | Augie: 'Ability to eliminate stuff that's not going to happen is as important as predicting what will.' Approach: analyze 10k+ non-funded loans for common failure patterns. | Feb 25, 2026
D-018 | Lock features must be used in combination with pipeline stage and days-at-stage — not as independent variables only. | Augie | Augie pushed for interaction features. A loan approved for 45 days + expiring lock = very different risk profile than approved 5 days + lock expiring in 25 days. Combination is the signal. | Feb 25, 2026
D-019 | Rolling 12-month training window is confirmed and locked in for both model versions going forward. | Team (Ajer/Liam) | Rolling window was the biggest improvement driver for Nov/Dec 2025 anomalies. Nov error: 28%→13%, Dec: 15%→6%. Fixed training window (2024 only) is retired. | Feb 25, 2026
D-020 | New error target set: reduce mid-month error from 4.8% toward 2-3%. | Augie | Current 4.8% beats the 10% internal target. Augie raised the bar: 'How do we improve from 4.8 to 2% or 3%?' This is the new quantitative benchmark. | Feb 25, 2026
D-021 | Strategic pivot: project focus shifts from model accuracy improvement to productization, packaging, and client-facing operational tools. | Augie | Augie: 'I'm okay living with 4.8%. Getting from 4.8 to 2% isn't revolutionary. Let's make it usable and turn this into actual client value.' Model building phase is largely complete. Delivery phase begins. | Mar 4, 2026
D-022 | 4.8% mid-month MAPE accepted as the production accuracy standard. Error reduction is no longer the primary objective. | Augie | Augie: 'I can live with 4.8%.' This supersedes the Call 3 target of 2-3%. The new goal is actionability, not precision for its own sake. | Mar 4, 2026
D-023 | Ajer and Liam will present directly to the CFO of the client company. Augie to arrange the meeting and potentially include the operations lead. | Augie | Augie: 'I want to put you guys in front of the CFO. It will be good experience and get real-world feedback.' Augie to coordinate timing and attendees. | Mar 4, 2026
D-024 | Operational loan tiering framework adopted: Dead (drop) / Watch (low probability) / Push (high probability, late stage). Replace first-in-first-out with probability-ranked pipeline. | Augie + Team | Augie vision + Liam/Ajer execution. Goal: reallocate client ops team effort from dead loans to high-probability ones. Business case: same volume with fewer resources. | Mar 4, 2026
D-025 | A LinkedIn podcast/article will be produced about the collaboration, using proxy company names (e.g. 'Falcon' for FlexPoint). | Augie | Augie proposed. Benefits for interns: LinkedIn presence and professional visibility. Benefits for Gallows: marketing. Company data anonymized per data policy. | Mar 4, 2026
D-026 | V3 model is the production version. It maintains 4.8% accuracy while adding pipeline hygiene, weekly timing, and failure archetype analysis. | Team (Ajer/Liam) | V3 adds 4 new capabilities over V2 without degrading accuracy: pipeline hygiene filter (4.7% with filter), 12 interaction features, weekly timing model, failure archetypes. Model building phase complete. | Mar 4, 2026
D-027 | Primary deliverable is now a mock dashboard / product prototype — not a further refined model. | Team (Ajer/Liam) + Augie | Ajer: 'We'll build a mock dashboard and show you, then transfer into Gallows.' This is the agreed next output. Model building is complete; product packaging begins. | Mar 25, 2026
D-028 | Primary end-user of operational tool is the Ops Manager, not the capital markets desk. Two different user types = two different products. | Augie | Augie: 'It would be the ops manager. His job is to go through loans as fast as possible.' Capital markets desk gets the monthly forecast. Ops manager gets the ranked loan list. Design accordingly. | Mar 25, 2026
D-029 | Broker Quality Score is adopted as a new core metric to build. Rank brokers by loan quality, pull-through, cycle time, and margin contribution. | Augie | Augie: 'Clients are not doing this at all — it's all gut feel.' Moneyball analogy. Hypothesis: 20% of brokers send 80% of trash. This is a differentiated, never-before-built metric for this client base. | Mar 25, 2026
D-030 | ROI framing for client pitch: 1% pull-through improvement = ~$400K additional revenue per $1B in loan volume at 400bps margin. This is the headline CFO number. | Augie (calculated live) | Augie computed this in real time on screen. Each funded loan = ~$13K revenue. Pull-through rate is the primary KPI to present to CFO. | Mar 25, 2026
D-031 | Model retraining data must tag loans dropped per model recommendation separately from loans that naturally failed. Required to prevent self-fulfilling prophecy bias. | Liam (identified) + Augie (confirmed) | Liam flagged the feedback loop risk unprompted. Augie validated it. Without this tagging, model will be artificially reinforced by its own recommendations. Critical for data governance going forward. | Mar 25, 2026
D-032 | Weekly meeting time to be rescheduled to early afternoon Wednesday (~3:30 PM) due to Ajer's new class conflict. To be confirmed via Slack. | Ajer + Augie | Ajer flagged schedule conflict. Augie confirmed early afternoons work. Coordination through Mariana. | Mar 25, 2026
D-033 | A live Claude AI working session will be held with Augie, Ajer, Liam, and Mariana to define product metrics, broker health scoring, and client-facing value positioning. | Augie | Augie: 'Let's do an actual working session with Claude. I'm happy to do an hour.' Augie offered to help with Claude access/license if needed. Scheduled for early week of Mar 30. | Mar 25, 2026
D-034 | Dashboard structure confirmed: (1) Headline KPIs — pipeline size, live/dead/projected, error rate; (2) Distribution by product/channel; (3) Watchlist — at-risk loans with per-loan specific reasons; (4) Live pipeline ranked by expected value; (5) Trends — pull-through rate + cycle times. | Augie (validated) + Team (built) | Augie: 'I like going from high-level to details.' Structure validated in Call 6. Team built all 4 tabs. Augie confirmed watchlist is the biggest money driver. Now in polish/iteration phase. | Apr 1, 2026
D-035 | Watchlist loans must have personalized, per-loan specific reasons — not generic labels. Each loan gets a specific flag (e.g. 'approved 151 days', 'rate lock expires in 7 days', 'pending final UW'). | Team (design choice confirmed by Augie) | Ajer: 'The design choice was that each loan should have a specific reasoning — personalized, not a generic at-risk label.' Augie validated this approach. | Apr 1, 2026
D-036 | Dashboard will remain in Claude/sandbox for further iteration and polish before being transferred to Gallows production environment. Gallows is the confirmed final front-end. | Augie + Team | Augie: 'We should be using Gallows for the front end.' Team: 'We just want to play around in sandbox first, then transfer.' Sequence: polish in sandbox → transfer to Gallows → connect DB → CFO demo. | Apr 1, 2026
D-037 | Presentation philosophy established: 'Not only WHAT you show, but HOW you show it.' Investment banking standard applies. Goal: go from solid start to brilliant analytical output. | Augie | Augie referenced investment banking presentation standards. Every visual must earn its place. Told Ajer directly: 'You're a future banker — sizzle matters.' Claude to be used as the tool for elevation. | Apr 1, 2026
D-038 | A shared Claude project workspace is the agreed collaboration infrastructure for the team going forward. | Augie + Ajer | Augie: 'Can we figure out a common workflow on Claude?' Ajer proposed shared project with all code, dashboard, and chat history. Augie: 'Send me the details and I can set up the instructions.' This replaces ad-hoc individual Claude usage. | Apr 1, 2026
D-039 | ThoughtSpot/Gallows access for Ajer and Liam is top priority. No more building outside the Gallows environment. | Augie | Augie: 'It doesn't make sense for Ajer and Liam to be building anything outside of ThoughtSpot.' Access granted live during Call 7. All future development to happen within Gallows. Mariana sent credentials during the call. | Apr 8, 2026
D-040 | Gallows enterprise Claude account access to be granted to Ajer and Liam for shared project workflow and agent development. | Augie | Augie: 'I'll give you guys a Gallows email and access to our enterprise account so you can work under a common workflow.' API key will also be available for agent development. Resolved at end of Call 7. | Apr 8, 2026
D-041 | Final project vision confirmed: build a Claude AI agent that provides full automated operational diagnosis of a mortgage company's pipeline with actionable insights and resource reallocation recommendations. | Augie | Augie: 'Before you go for summer, let's create an agent working 24/7 for us. A really cool diagnosis methodology for the health of the ops department with actionable insights.' This is the ultimate deliverable. Sub-agent architecture recommended. | Apr 8, 2026
D-042 | All model conclusions and dashboard recommendations must be red-teamed using AI (Claude/ChatGPT as industry expert) before client presentation. | Augie | Augie: 'Red team the hell out of them. The CIA does this — teams whose job is to disprove conclusions so we don't bomb the wrong house.' This is a mandatory validation step. Liam suggested building it into the dashboard via API call. | Apr 8, 2026
D-043 | Dashboard philosophy: go beyond the x-ray (diagnosis) to the full prescription (actionable recommendations per loan). Do not stop at showing data — show what to DO about it. | Augie | Augie: 'I don't want to stop at the x-ray. I want the full diagnosis — you have a broken leg, put a cast, go to rehab, the whole thing.' Every risk identified must have a corresponding action with quantified probability improvement. | Apr 8, 2026
D-044 | Balanced Scorecard approach adopted: agree on KPIs, assign weights, compute a single composite health score per product type. Track over time. | Augie | Augie: 'Create a balanced scorecard — a number that is the balanced result of all the KPIs. Then if conforming drops from 7.7 to 7, I know something is wrong.' Requires alignment on KPI weights. Non-conforming confirmed as top performer. | Apr 8, 2026
D-045 | Medians alone are insufficient — all cycle time and conversion metrics must show variance (IQR, box plots, or std dev), broken down by product. | Augie | Augie: 'Averages are for wimps — medians can hide big variance. A good median with 20% of customers getting terrible service is not good.' Domino's pizza analogy. IQR or Q1/Q3 to be added to all distribution charts. | Apr 8, 2026
D-046 | Project management: Mariana to compile a master priority/hierarchy document from all call recordings. This will be the official shared to-do tracker going forward. | Augie | Augie: 'Mariana, let's put all our to-dos, create a list of priorities and hierarchy — I don't want ideas getting lost in the shuffle.' Mariana to review recordings and compile with Augie. Then shared with Ajer/Liam. | Apr 8, 2026

## Improvements & Requests
IMPROVEMENTS & FEATURE REQUESTS
Request ID | Description | Priority | Status | Notes
R-001 | Add 'product' variable to predictive model (Fannie/Freddie conventional vs. Government/FHA loans) | High | Completed | Fully decoupled and independently visible in V2 model. Non-conforming purchase=60%, FHA purchase=64%, refi cashout=47%. Signal still embedded in pipeline stage but now transparent.
R-002 | Add 'purpose' variable to predictive model (Purchase vs. Refinance) | High | Completed | Added and validated in Call 2. Embedded in pipeline stage feature currently. Decoupling required.
R-003 | Increase sophistication of model by differentiating pipeline stage probabilities by loan product and purpose (instead of a single generalized probability) | High | Completed | Stratified transition tables built from 15,000+ loans. Stage × product × purpose probabilities computed. Cell sizes under 20 loans smoothed back to stage-only probability.
R-004 | Develop back-testing framework: predict a historical quarter using only prior data, then compare predicted vs. actual fundings | High | Completed | Full framework complete. 24-month backtest, rolling window, correct snapshot methodology. Nov still slightly above 10% but significantly improved. Framework validated.
R-005 | Integrate funding volume projections with P&L and balance sheet modeling to provide clients full financial picture | Medium | In Progress | Augie showed corporate finance model live. Confirmed as next major milestone after model stabilization and ThoughtSpot integration.
R-006 | Apply machine learning techniques (e.g., random forest) to assess variable importance and predictive power | Medium | Completed | Gradient boosting (V2) running. V2 outperforms V1 on all metrics: 4.8% vs 6.4% avg error, 23/24 months vs 18/24 within target.
R-007 | Whitelist campus Wi-Fi IP address for Ajer and Liam to enable database access from university network | High | Completed | IP shared live during the call. Mariana/Israel to action. Both team members currently limited to apartment IP.
R-008 | Add Liam to the Forecasting Slack channel | Medium | Completed | Augie is admin. Request raised at end of call by Liam. Israel was already added previously.
R-009 | Add rate lock date and lock expiration date as model features. Compute: (1) days until lock expires, (2) days since lock was created | High | Completed | 5 new lock features built. Lock expiry vs month end = 60% model weight in V2. Error reduced to 4.8%. Augie confirmed Version B (with lock). Closed.
R-010 | Fix model calibration: mid-range probability loans (~55%) are over-confident; actual funding rate is ~40-47%. Apply statistical recalibration. | Medium | Pending – Future Phase | Augie accepted 4.8% as production standard in Call 4. Formal recalibration deprioritized. May revisit if needed post-CFO meeting.
R-011 | Investigate and add seasonality variable (month of year / quarter) to capture summer vs winter funding speed differences | Medium | Completed | Fully tested. Summer pull-through=41% vs winter=36%. Volume 25% higher. Speed FLAT year-round. Incorporated into timing model stage durations.
R-012 | Build automated daily scoring pipeline: model scores all active loans → writes to DB → ThoughtSpot refreshes projections automatically | High | In Progress | 1-2 week effort per team. Scoring module already in ThoughtSpot format. Augie shifted focus to packaging first. DB pipeline next after CFO presentation.
R-013 | Grant ThoughtSpot FlexPoint org access to Ajer and Liam for visualization and Muse Studio experimentation | High | Open | Augie committed. Mariana to coordinate. AI-019.
R-014 | Isolate product and purpose as independent features in the model (decouple from pipeline stage probability feature) | High | Completed | Augie: clients need to see individual variable coefficients. Currently embedded in 59.5% pipeline feature. AI-015.
R-015 | Build interaction feature: lock expiry proximity × days at current stage × pipeline stage (3-way combination for failure/success prediction) | High | Completed | 12 interaction features built. GBM already discovering combinations internally — features improve transparency/auditability. MAPE unchanged at 4.8%.
R-016 | Build loan elimination rules: identify patterns in non-funded loans (e.g. stuck in underwriting + lock expiring + low credit) and filter them out of projections with 90%+ confidence | High | Completed | Pipeline hygiene filter complete. 46% of active pipeline flagged as dead. Zero false negatives across 128 snapshots. 3 specific elimination rules defined. Error tightens to 4.7% with filter.
R-017 | Build day-of-month / week-of-month timing prediction: predict WHEN each loan will fund, not just IF. Use pipeline stage, days-at-stage, and end-of-month spike patterns. | High | Completed | Weekly timing model built. 38% of volume last week. GBM 2.8 days MAE per loan. Hybrid: historical distribution at day 0, GBM from day 8+.
R-018 | Reduce mid-month model error from 4.8% to 2-3% through combination of elimination rules, interaction features, and timing prediction | High | Pending – Future Phase | Augie Call 4: 'Getting from 4.8 to 2% isn't revolutionary.' Target downgraded. 4.8% accepted. Focus shifted to productization.
R-019 | Build and deliver client-facing operational dashboard: loan tiers (Dead/Watch/Push), pipeline hygiene score, kill zone visualization, weekly timing forecast. | High | In Progress | V2 dashboard presented in Call 7 with 6 tabs: Overview, Watchlist, Live Pipeline, Revenue at Risk (new), Pipeline Health (new), What-If Levers (new), Scorecards (new). Augie: positive feedback. Still iterating — add variance, benchmarks, action recommendations, balanced scorecard.
R-020 | Obtain lock extension / relock history data from FlexPoint to improve elimination filter precision and timing model. | High | Open | Currently proxied. Real data would improve accuracy of loan survivability predictions. AI-035. Request to be made by Mariana/Israel to FlexPoint.
R-021 | Produce LinkedIn podcast/article using anonymized company name ('Falcon'). Document the UChicago × Gallows data science collaboration. | Medium | Open | Augie-initiated. Good for intern professional profiles and Gallows marketing. Proxy names required. AI-034.
R-022 | Prepare CFO-ready presentation: business value of pipeline hygiene, kill zone, loan prioritization, and timing prediction. Frame in terms of cost reduction and pull-through rate improvement. | High | In Progress | Dashboard V2 is the pitch asset. Agent + red-team validation needed before CFO meeting. No date set. Timeline constrained by summer internship start (June).
R-023 | Build mock dashboard prototype with: loan prioritization tiers, pull-through rates by product, cycle time distributions (app-to-funding), broker quality scores. Designed for ops manager Monday-morning use. | High | Open | Primary next deliverable agreed in Call 5. Will be the basis for the CFO presentation and Gallows integration. AI-038, AI-042.
R-024 | Build 'Broker Quality Score' metric: rank by pull-through rate, cycle time, loan exception rate, margin per loan. Flag low-quality high-volume brokers. | High | Open | Augie: completely untracked by clients today. 20%/80% hypothesis. Moneyball analogy. New differentiating metric. AI-040.
R-025 | Analyze loan profitability distribution by product (basis points earned). Identify why wide variance exists within same product type. Link to cycle time and broker data. | Medium | Open | Augie showed live box plot: non-QM ranged 240–518bps on same product. Wide variance unexplained. Requires cycle time and broker relationship analysis. Q-025 still unanswered. AI-039.
R-026 | Build CFO-ready ROI calculator: pull-through rate improvement → incremental volume → revenue at 400bps margin. Input: current volume and pull-through %. Output: $ revenue uplift. | High | Open | Augie calculated: $400K per 1% improvement per $1B volume. Each loan = ~$13K. This is the CFO hook. AI-041.
R-027 | Implement data governance tagging: flag loans abandoned per model recommendation vs. loans that naturally failed. Required to prevent model feedback loop bias during retraining. | High | In Progress | Not yet implemented. Partially addressed by loss analysis concept and recovery opportunities table. Full tagging in data pipeline still pending.
R-028 | Add 'Loss Analysis' tab to dashboard: track eliminated loans, flag false positives (loans model killed that would have funded), document root cause of lost revenue. Each unfunded loan = $13K lost. | High | Open | Augie: 'Document the ones that shouldn't have been eliminated.' Closes the feedback loop. Links to AI-027 (data governance tagging) and AI-048. Critical for model accountability and client trust.
R-029 | Elevate dashboard visual design: headline KPIs at top, consistent color scheme (gray=total, blue=live), investment-banking-grade layout and polish. Use Claude for rapid iteration. | High | Open | Augie: 'Go from solid start to brilliant.' Presentation quality = investment banking standard. AI-050. Fix color bug (AI-046) as first step.
R-030 | Set up shared Claude team project for Augie, Ajer, Liam, Mariana with all model code, dashboard code, and chat history in one shared context. | Medium | Open | Augie confirmed this is the collaboration infrastructure going forward. Blocked on setup instructions. AI-049. Ajer to send setup guide to Augie.
R-031 | Investigate and fix data quality issue: conforming loan on watchlist showing as unlocked at CTC stage. Likely mislabeling of non-QM as conforming. | High | Open | Augie flagged live in Call 6. Must be resolved before any client-facing demo. Credibility risk if wrong data appears on watchlist. AI-047.
R-032 | Add per-loan action recommendations to dashboard: for each at-risk loan, show specific action + estimated probability increase (e.g. 'Get lock → probability 7%→61%'). Bridge from diagnosis to prescription. | High | Open | Augie: 'Tell them the action AND the impact on probability.' Core product value proposition. AI-052. Pre-requisite for CFO pitch.
R-033 | Build 2×2 bubble matrix: Y=funding probability, X=execution difficulty, bubble size=loan amount. Highlight quick-win quadrant (high probability + low effort). Mark loans that can move quadrants with simple actions. | High | Open | Augie: 'Pick the chips on the roulette that give highest probability with least effort.' Upper-left quadrant = priority. AI-053. Moneyball framework applied to loan prioritization.
R-034 | Add variance metrics to all cycle time and conversion charts: IQR, box plots, or Q1/Q3/median. Break down by product. Remove median-only views. | High | Open | Augie: 'Medians hide variance. Competitive medians AND low variance is the goal.' Domino's analogy. AI-054.
R-035 | Build Balanced Scorecard composite KPI per product: weighted combination of pull-through rate, cycle time, loan size, volume, revenue efficiency. Track over time. | High | Open | Augie: 'I want a single number that is the balanced result of all KPIs.' Enables instant health-check per product. AI-056.
R-036 | Research and integrate industry benchmark cycle times per product type (VA, FHA, conventional, non-QM) to contextualize whether observed times are good or bad. | Medium | Open | Augie: 'VA at 20 days might not be bad — VA is more complicated than FHA.' Need product-specific benchmarks. Use Claude/ChatGPT to source. AI-055.
R-037 | Build a Claude AI agent using Anthropic API (Gallows enterprise key): autonomous pipeline diagnosis, actionable insights, resource reallocation recommendations. Use sub-agent architecture. | High | Open | Augie's ultimate deliverable before summer. AI-058. Sub-agents to silo processes and reduce hallucination. Liam suggested red-teaming API call as sub-agent within dashboard.
R-038 | Build red-teaming validation step: prompt Claude/ChatGPT as mortgage ops expert to challenge all data conclusions before client presentation. Consider building as an API call within the dashboard. | High | Open | Augie: 'Red team the hell out of them before showing clients.' Mandatory validation step. AI-057. Liam: could be embedded as real-time API sub-agent.

## Call Log
CALL LOG & SUMMARIES
Call # | Date | Participants | Key Topics Summary
Call 1 | Apr 14, 2026 | Speaker 1 (Mariana / Israel), Speaker 2 (Augie), Ajer, Liam | 1. Overview of existing predictive model: current variables (amount, channel, loan type), time windows (28/30/31 days), and pipeline stage probabilities. 2. Database access confirmed; IP whitelist request for campus Wi-Fi submitted. 3. Augie explained loan pipeline stages (submitted → processing → conditional approval → completion → funding requested → funded → purchased by investor) and mutual exclusivity. 4. Business objective clarified: predict remaining monthly funding volume ($ amount) for retail and wholesale channels. 5. Augie demonstrated ThoughtSpot FlexPointScore dashboard showing current forecast output (e.g., $118M projected for Feb; $38.6M already funded). 6. Key improvement direction: add product (Fannie/Freddie vs. Govt) and purpose (purchase vs. refi) variables first. 7. Methodology discussion: run 3–5 models, back-test on historical data, focus on most explanatory variables only. 8. Weekly Wednesday cadence confirmed. Slack channel established for async comms. 9. Team next steps: extract full dataset in Python, run correlation/covariance analysis, identify top variables, iterate on model.
Call 2 | Feb 18, 2026 | Speaker 1 (Augie / Mariana), Speaker 2 (Ajer / Liam) | 1. DEMO PRESENTATION by Ajer & Liam: showed completed work since Call 1. 2. Data pull confirmed complete — full SQL database extracted in Python. 3. Product & purpose variables added and validated (59pp shift in funding probabilities confirmed). 4. Feature importance results: pipeline stage = 59.5%, days at stage = 9.9%, days remaining in month = 8.4%, credit score/loan amount/lock period = 3-4% each. 5. Back-test results: 24 months tested (2024-2025). Avg mid-month error = 6.4%. 18/24 months within 10%. Nov/Dec 2025 outliers: 28% and 16% over-projection. 6. Two models running: transition table + gradient boosting ML. 7. Augie feedback: (a) fix back-test snapshot methodology, (b) decouple product/purpose from pipeline feature, (c) add lock date / lock expiration date, (d) investigate Nov/Dec anomaly, (e) add slide footnotes. 8. Rate lock discovery: locked loans fund 79% vs <1% unlocked. Augie explained lock mechanics and confirmed it is a strong predictor. 9. Augie introduced seasonality hypothesis (summer vs winter closings). 10. ThoughtSpot access to be granted; Muse Studio visualization discussed. 11. End goal reconfirmed: projections → DB pipeline → ThoughtSpot → P&L/balance sheet integration for clients. 12. Augie: 'Really impressive. Very well presented.' Only feedback was footnotes on slides.
Call 3 | Feb 25, 2026 | Speaker 1 (Ajer / Liam / Mariana), Speaker 2 (Augie) — Augie joined late | 1. V2 MODEL DEMO: Ajer & Liam presented full V2 update. 2. Product & purpose decoupled as independent features. Non-conforming purchase=60%, FHA=64%, refi cashout=47%. Signal visible but standalone weight small (embedded in pipeline stage). 3. Rate lock features: 5 new features built around lock date/expiry. Lock expiry vs month end = 60% model weight. Mid-month error improved 6.5%→4.8%. 4. Back-test: 24 months tested. Avg mid-month error=4.8% (was 6.4%). 23/24 months within 10% (was 18/24). 25% error reduction vs V1. 5. Snapshot fix implemented: all months use end-of-prior-month pipeline. Dec←Nov30, Nov←Oct31. 6. Rolling 12-month window confirmed as biggest improvement driver for Nov/Dec anomalies. Nov: 28%→13%, Dec: 15%→6%. 7. Seasonality tested: summer=41% pull-through vs winter=36%. Volume 25% higher in summer. KEY: days-to-fund is FLAT year-round (conversion rate shifts, not speed). 8. Two paths presented: Version A (no lock, 6.5% error) vs Version B (with lock, 4.8% error). 9. AUGIE DECISION: Version B chosen. 'Version A shouldn't exist — silly not to use lock data.' 10. Augie new directions: (a) build interaction features (lock+stage+days-at-stage), (b) build loan elimination rules from non-funded loan patterns, (c) build timing prediction (WHEN loans fund). 11. New target: reduce error from 4.8% to 2-3%. 12. End-of-month spike confirmed in ThoughtSpot: week 4=$735M vs week 3=$672M. 13. Integration: scoring module already outputs ThoughtSpot format. DB pipeline = 1-2 week effort. Waiting for model stabilization. 14. Augie missed first ~20 min — slide deck sent to his email during call. Recording to be sent after.
Call 4 | Mar 4, 2026 | Speaker 1 (Ajer), Speaker 2 (Augie), Speaker 3 (Liam) — 3 speakers confirmed | 1. V3 MODEL DEMO presented by Ajer & Liam. 2. INTERACTION FEATURES: 12 features built (lock×stage, velocity, lock extension proxies). GBM already discovers combinations internally — features improve transparency. MAPE unchanged at 4.8%. 3. PIPELINE HYGIENE FILTER: 46% of active pipeline = dead weight. Zero false negatives across 128 backtest snapshots. 3 elimination rules defined. Error tightens to 4.7% with filter. 4. FAILURE ARCHETYPES: 9,611 failed loans segmented. 44.6% early dropouts, 7.6% pre-approval stall, 7.6% approved+never locked, 3.4% lock expired, 1.5% late-stage surprise. 94% of failures die at or before 'approved' = Kill Zone. 5. TIMING MODEL: 38% of volume lands in last week (structural backloading). Week distribution: 18/21/23/38%. GBM 2.8 days MAE per loan. Hybrid approach: historical at day 0, GBM from day 8. 6. STAGE DURATIONS: CTC→funded=5 days median; Approved→funded=24 days (wide IQR 18-33); Submitted/Opened→funded=~29 days. Speed flat year-round. 7. BACKTEST V3: 4.8% mid-month, 23/24 months within 10%, model stable even as volumes ramped 100M→175M in H2 2025. 8. AUGIE STRATEGIC PIVOT: 'I can live with 4.8%. Let's shift from model building to making it usable.' Focus = productization, operational tools, CFO presentation. 9. NEW AUGIE DIRECTION: Build operational loan tiering (Dead/Watch/Push). Replace first-in-first-out with probability-ranked queue. Business case = same output with less labor. 10. CFO MEETING: Augie will arrange for Ajer & Liam to present directly to client CFO (+ possibly ops lead). 11. LINKEDIN PODCAST: Augie proposed publishing collaboration article using proxy names ('Falcon'). Good for all parties. 12. TERMINOLOGY COINED: 'Pipeline Hygiene', 'Kill Zone' — Augie wants rich, branded outputs. 13. LOCK EXTENSIONS: Dataset doesn't track relocks. Requested from FlexPoint to improve filter. 14. Augie: 'A lot better than most MBAs can deliver. Really, really great work.'
Call 5 | Mar 25, 2026 | Speaker 1 (Augie), Speaker 2 (Ajer/Liam) — 2 speakers (34 min) | 1. FEEDBACK LOOP RISK: Liam raised self-fulfilling prophecy concern — if model tells ops to drop loans and they do, model is reinforced regardless of whether it was actually right. Solution: tag dropped-per-recommendation loans separately in data. Augie validated. 2. LOAN PRIORITIZATION DEMO: Augie demonstrated expected value prioritization using Excel live — with limited underwriters, prioritize loans by probability × loan amount. With finite resources (2 underwriters, 5–7 loans), expected value of top-ranked selection vs random = significantly higher. 3. BUSINESS VALUE QUANTIFIED: 1% pull-through improvement per $1B volume = ~$400K additional revenue at ~400bps margin. Each funded loan = ~$13K revenue. Pull-through rate confirmed as the primary CFO-level KPI. 4. VIRTUOUS CYCLE: Faster cycle times → better broker experience → broker sends more loans → higher volume. Speed is the differentiator in wholesale (price is commoditized). 5. BROKER QUALITY SCORE: Augie introduced concept — rank brokers by loan quality, pull-through, cycle time, margins. Industry does NOT do this (all gut feel). Moneyball analogy. 20%/80% hypothesis (20% of brokers send 80% of bad loans). 6. PULL-THROUGH RATES SHOWN LIVE: Augie showed Gallows dashboard with real client data — conventional=50.8%, HELOC=36%, QM=9.1%. Wide cycle time variance by product. 7. PROFITABILITY VARIANCE: Augie showed box plot of profitability by product — same non-QM product ranged 240–518 bps. Unexplained variance. 'Averages are for wimps — manage the distribution.' 8. END-USER DEFINED: Ops Manager = primary user. Opens dashboard Monday morning. Needs ranked actionable loan list. Capital markets desk = different user (monthly forecast). 9. MOCK DASHBOARD AGREED: Team will build a mock product prototype first, then transfer analytics into Gallows. Mock to be shown to Augie before CFO pitch. 10. CLAUDE WORKING SESSION: Augie proposed 1-hour live session with Claude + full team early week of Mar 30. Use Claude to define metrics, broker scoring, client positioning. Augie offered Claude license help if needed. 11. MEETING RESCHEDULE: Ajer has new class at this time slot. Proposed 3:30 PM Wednesday. Augie OK with early afternoons. To be confirmed via Slack with Mariana. 12. AUGIE: 'I don't even know why this hasn't been solved yet.' Confirmed the industry runs entirely on gut feel and first-in-first-out queues.
Call 6 | Apr 1, 2026 | Speaker 1 (Augie / Mariana), Speaker 2 (Ajer) — 15 min, shortest call to date | 1. GALLUS/THOUGHTSPOT ACCESS — Resolved immediately. Augie made it top priority at call start. Mariana sent login email to Ajer and Liam live during the call. No more building outside Gallus. 2. DASHBOARD V2 DEMO — Major upgrade from Call 6. New tabs added: • Weekday Actions: 6 ranked recommendations with dollar estimates shown first on load • Overview: total pipeline, live, eliminated, projected funding, error rate, funnel by stage, channel/product breakdown • Watchlist: 59 flagged loans with per-loan risk reasons and probability shown • Live Pipeline: ranked by expected value • Revenue at Risk (NEW): $145M at risk in 4 categories — (1) Stalled high-value: 97 loans / $79M / 30+ days stalled; (2) Low prob high value: 47 loans / $64M / <25% prob; (3) Lock expiring: 7 loans / $1.5M within 7 days; (4) No lock late stage: 3 loans / $443K. Top 12 recovery opportunities table — $10.4M total recovery potential. • Pipeline Health (NEW): stage transition heatmap by product, conversion funnel, velocity distribution (fast/on pace/stalled), bottleneck chart (41% of approved loans >30 days), momentum alerts table • What-If Levers (NEW): 4 operational levers with $ impact — (1) Improve lock rate: ~$22M; (2) Accelerate approved-to-CTC: ~$98M; (3) Reactivate stale: ~$5.8M; (4) Retail optimization: ~$700K. Total ~$40M = 127% above current projection • Scorecards (NEW): product vs product comparison — pull-through, cycle time, avg loan size, volume, revenue efficiency. Non-conforming = #1 performer (40% pull-through, $572K avg, highest efficiency) 3. AUGIE KEY FEEDBACK: (a) Add action recommendations per loan with probability delta; (b) Build 2×2 bubble matrix (probability vs difficulty, bubble=loan amount); (c) Add variance metrics (IQR/box plots) — 'medians alone are for wimps'; (d) Add product benchmarks for context; (e) Build balanced scorecard composite KPI; (f) Red-team all conclusions with AI as ops expert. 4. STRATEGIC SHIFT — AGENT BUILD: Augie: 'Before you go for summer, let's create a Claude agent working 24/7.' Goal: autonomous ops health diagnosis + actionable insights. Sub-agent architecture. Anthropic API key from Gallows enterprise account. 5. CLAUDE ENTERPRISE ACCESS: Augie to give Ajer/Liam Gallows email + enterprise Claude access. Shared project workflow finally unblocked. 6. RED-TEAMING: Augie introduced concept — prompt AI as mortgage ops expert to disprove conclusions before client presentation. Liam: could be built as real-time API sub-agent in dashboard. 7. SUMMER TIMELINE: Ajer and Liam start internships in June. Only ~3 days between UChicago end (late May) and internship start. ~6-7 weeks remaining. Augie wants to be respectful of timeline. 8. INTERN PIPELINE: Augie asked for 2-3 serious UChicago interns (UMAG) to continue work in summer. Both Ajer and Liam confirmed they are in UMAG. 9. PROJECT MANAGEMENT: Augie asked Mariana to compile master priority/hierarchy document from all call recordings tomorrow. 10. SOCIAL: Tennis + dinner Monday Apr 13 — Augie, Ajer (tennis at 8am), Liam (dinner at Quadrangle Club 6-7pm, then EBC). AUGIE CLOSING: 'You guys are gonna have a better resume than me by the time this is done. Really, really cool work.'
Call 7 | Apr 8, 2026 | Ajer Sher, Liam Harvey, Agustin (Augie) via iPhone, Mariana Arroyo — ~41 min. FINAL CALL. | 1. GALLUS/THOUGHTSPOT ACCESS — Resolved immediately. Augie made it top priority at call start. Mariana sent login email to Ajer and Liam live during the call. No more building outside Gallows. 2. DASHBOARD V2 DEMO — Major upgrade from Call 6. New tabs added: • Weekday Actions: 6 ranked recommendations with dollar estimates shown first on load • Overview: total pipeline, live, eliminated, projected funding, error rate, funnel by stage, channel/product breakdown • Watchlist: 59 flagged loans with per-loan risk reasons and probability shown • Live Pipeline: ranked by expected value • Revenue at Risk (NEW): $145M at risk in 4 categories — (1) Stalled high-value: 97 loans / $79M / 30+ days stalled; (2) Low prob high value: 47 loans / $64M / <25% prob; (3) Lock expiring: 7 loans / $1.5M within 7 days; (4) No lock late stage: 3 loans / $443K. Top 12 recovery opportunities table — $10.4M total recovery potential. • Pipeline Health (NEW): stage transition heatmap by product, conversion funnel, velocity distribution (fast/on pace/stalled), bottleneck chart (41% of approved loans >30 days), momentum alerts table • What-If Levers (NEW): 4 operational levers with $ impact — (1) Improve lock rate: ~$22M; (2) Accelerate approved-to-CTC: ~$98M; (3) Reactivate stale: ~$5.8M; (4) Retail optimization: ~$700K. Total ~$40M = 127% above current projection • Scorecards (NEW): product vs product comparison — pull-through, cycle time, avg loan size, volume, revenue efficiency. Non-conforming = #1 performer (40% pull-through, $572K avg, highest efficiency) 3. AUGIE KEY FEEDBACK: (a) Add action recommendations per loan with probability delta; (b) Build 2×2 bubble matrix (probability vs difficulty, bubble=loan amount); (c) Add variance metrics (IQR/box plots) — 'medians alone are for wimps'; (d) Add product benchmarks for context; (e) Build balanced scorecard composite KPI; (f) Red-team all conclusions with AI as ops expert. 4. STRATEGIC SHIFT — AGENT BUILD: Augie: 'Before you go for summer, let's create a Claude agent working 24/7.' Goal: autonomous ops health diagnosis + actionable insights. Sub-agent architecture. Anthropic API key from Gallows enterprise account. 5. CLAUDE ENTERPRISE ACCESS: Augie to give Ajer/Liam Gallows email + enterprise Claude access. Shared project workflow finally unblocked. 6. RED-TEAMING: Augie introduced concept — prompt AI as mortgage ops expert to disprove conclusions before client presentation. Liam: could be built as real-time API sub-agent in dashboard. 7. SUMMER TIMELINE: Ajer and Liam start internships in June. Only ~3 days between UChicago end (late May) and internship start. ~6-7 weeks remaining. Augie wants to be respectful of timeline. 8. INTERN PIPELINE: Augie asked for 2-3 serious UChicago interns (UMAG) to continue work in summer. Both Ajer and Liam confirmed they are in UMAG. 9. PROJECT MANAGEMENT: Augie asked Mariana to compile master priority/hierarchy document from all call recordings tomorrow. 10. SOCIAL: Tennis + dinner Monday Apr 13 — Augie, Ajer (tennis at 8am), Liam (dinner at Quadrangle Club 6-7pm, then EBC). AUGIE CLOSING: 'You guys are gonna have a better resume than me by the time this is done. Really, really cool work.'